## README
JOBBees — Scope Reconciliation Workbook
Booklet (13-sprint MVP plan) vs Feature Estimation v1.2 vs Test Plan v2.0
Purpose | Re-sync the three planning artifacts. Every item the cross-check found missing or changed is listed with a column for the developer to declare its true status (Deferred / Dropped / Covered-elsewhere / Will-add) and a destination. Once filled, the estimate, booklet and test plan agree.
How to use | Work the GAP REGISTER tab top to bottom. For each row set 'Dev Decision' from the dropdown, name the Destination (sprint, V2, or N/A), and add a note. Severity and the architect's recommendation are pre-filled.
Tabs | GAP REGISTER — the fill-in table (28 items). COVERAGE MAP — all 8 estimate components vs booklet status. CHANGED ITEMS — features built differently. TEST IMPACT — what each gap does to the test suite. SIGN-OFF — founder + dev acceptance block.
Decision values | DEFERRED = agreed post-MVP, must appear in booklet appendix + be removed from MVP estimate. DROPPED = cut permanently, remove from estimate. COVERED = already built elsewhere, point to where. WILL-ADD = reinstating into a named sprint.
Severity key | HIGH = launch/quality/compliance risk at any scale. MEDIUM = matters at self-serve scale or for growth. LOW = convenience / polish.
Source of truth | Estimation v1.2 (394 in-scope rows) + JOBBees MVP Sprint Detail Booklet (S0 + 12 build sprints, 1 Jun–4 Dec 2026) + Master Test Plan v2.0 (481 TCs).
Bottom line | The booklet fully delivers the transactional core. Two funded components (Flutter Web 18 items, Next.js SEO 18 items) and the AI-operations layer (observability, eval harness, cost quotas) have no sprint and are not in the post-MVP appendix. Plus behavioural fraud scoring and two-person financial controls are absent. None block a one-suburb soft launch; all matter at self-serve scale.

## GAP REGISTER
GAP REGISTER — items missing or unaccounted-for in the booklet
Fill the three right-hand columns (shaded). Dropdown in 'Dev Decision'.
# | Est. ID(s) | Item / Feature | Component | Est. Call | Booklet status (architect finding) | Severity | Architect recommendation | DEV DECISION ▼ | Destination (sprint / V2 / N/A) | Dev note / justification
1 | SEO-01..19 | Next.js SEO public site (whole component) | 5. Next.js SEO | IN×18 | No sprint builds it. Only 'How it works' page on public web (S11) + one mention in S11 intro. Not in post-MVP appendix. | MEDIUM | Confirm deferral & add to appendix, OR schedule. No organic acquisition channel without it; programmatic location×category pages are a primary low-CAC growth engine.
2 | FW-01..18 | Flutter Web app (whole component) | 4. Flutter Web | IN×18 | Mobile-only launch (TestFlight + Play S11). No web build in any sprint. Not in post-MVP appendix. | LOW-MED | Confirm deferral & add to appendix. App-only soft launch is defensible; note cookie-consent/a11y (FW-13/14) still legally required if any web surface exists.
3 | AI-02 | LLM observability (Langfuse / Helicone) | 6. AI Infra | IN | Not mentioned in any sprint. No trace/cost visibility on AI calls. | HIGH | Reinstate. Without it there is no way to see prompt behaviour or cost in prod for an AI-dependent product.
4 | AI-03 | Prompt versioning + A/B eval harness | 6. AI Infra | IN | Not mentioned. No eval gates on prompt changes. | HIGH | Reinstate. Test Plan AI-eval gates (locked S3->S9) CANNOT run without this; blocks safe AI iteration.
5 | AI-12 | AI cost quota enforcement | 6. AI Infra | IN | Not mentioned. No per-user / org cost ceiling. | HIGH | Reinstate. Protects against cost runaway; NFR-C01 cost test depends on it.
6 | B-48 | Behavioural fraud scoring | 2.10 Trust&Safety | IN★ | Absent. Fraud posture = EXIF tamper-check + Azure Content Safety only. No device/velocity/graph signals. | HIGH | Reinstate or accept risk in writing. Was critical (IN★). Marketplace collusion / multi-account fraud undetected.
7 | AP-56 | Two-Person Approval Rule (maker-checker) | 3.14 Admin | IN | Absent — follows from single-admin-role decision. No four-eyes on refunds/fees. | MEDIUM | Confirm acceptable. Financial-controls gap: high-value refunds and fee changes have no second approver.
8 | AP-52 | Ad-hoc Report Builder (NL queries + export) | 3.11 Admin | IN★ | Absent. No natural-language report builder. | LOW | Defer acceptable. Visual reports suffice early; was IN★ but non-critical for soft launch.
9 | 217 | Product analytics instrumentation (PostHog/Mixpanel) | 1.18 Cross-cut | IN | Only Azure App Insights (ops monitoring) mentioned. No product-event/funnel analytics. | MEDIUM | Instrument day-one. Deferred funnel/LTV/churn dashboards (appendix) will have NO historical data without events flowing now.
10 | AI-07 | Auto-SEO content generation per task | 6. AI Infra | IN | Not mentioned (ties to missing SEO layer). | LOW | Defer with SEO site. Only relevant once public pages exist.
11 | AI-05 | Feature store (matching + pricing ML) | 6. AI Infra | THIN | Not mentioned. Matching works without a formal feature store. | LOW | Defer acceptable. Embeddings + ranker function without it at MVP scale.
12 | 194 | RAG support agent (chat) | 1.16 Support | IN | Support = email at MVP (stated in appendix). RAG agent deferred. | LOW | Already deferred in appendix — confirm only. Acceptable substitution.
13 | B-53 / B-23 | Message moderation: LLM classifier -> regex | 2.5/2.10 | IN | Booklet uses regex off-platform detection (S5), not Gemini-Flash LLM classifier. | MEDIUM | Confirm intent. Regex misses coded variants ('zero four one two', unicode, 'find me on the gram'). Add evasion corpus; reframe AIE-004 as regex-coverage.
14 | AP-53 | Super User Dashboard: 24-tile -> simpler KPI | 3.12 Admin | IN | Booklet = KPI overview + system-health panel (S9), simpler than 24-tile spec. | LOW | Accept. Present in spirit; full tile set can follow.
15 | AP-51 | Automated reports: full suite -> daily reconciliation | 3.11 Admin | IN | Booklet details daily reconciliation; weekly/monthly not enumerated. | LOW | Confirm weekly/monthly still in. Crons cheap to add.
16 | AP-04(KYC) | KYC: manual identity review -> Stripe Connect handles all | 1.2/3.2 | IN | Identity verification fully delegated to Stripe Connect. Manual identity queue eliminated (items 21/22 gone). | MEDIUM | Accept (clean resolution). Verify Connect verification states correctly gate bidding/payout — now the sole identity trust-gate.
17 | AI-04 | Output guardrails: general validator -> mediator cost-guard only | 6. AI Infra | IN | Only mediator has explicit cost guardrails (S7). No general output-validation layer across AI surfaces. | MEDIUM | Reinstate validators. Extraction/vision/support outputs need schema + safety validation, not just cost caps.
18 | B-51 | Prompt injection defense + PII scrubbing | 2.10 | IN | Partial — 'security review skill' + implied PII scrubbing; no explicit injection-defense feature across AI surfaces. | MEDIUM | Make explicit. Every AI surface (extraction, mediation, support, NL) needs injection hardening + PII scrub tests.
19 | 206 | Deep linking (Universal/App Links) | 1.18 Cross-cut | IN | Implied by S11 polish + S3 share-link; not individually listed. | LOW | Confirm built. Needed for share links + notification taps.
20 | 216 | Crash reporting (Sentry SDK) | 1.18 Cross-cut | IN | App Insights mentioned (S10) for backend; client crash SDK not explicit. | LOW | Confirm client crash capture present.
21 | 223 | Push token rotation | 1.18 Cross-cut | IN | Notifications built S8; token rotation not explicit. | LOW | Confirm handled.
22 | 210 / 211 | Maintenance mode screen / offline indicator | 1.18 Cross-cut | THIN/IN | Not individually listed; 'status page (thin)' S10 only. | LOW | Confirm or defer.
23 | 218 | Accessibility basics (WCAG 2.1 AA) mobile | 1.18 Cross-cut | THIN | Web a11y absent (no web); mobile a11y not explicitly called out. | MEDIUM | Confirm mobile a11y in scope. Compliance-adjacent.
24 | B-19/AP-44 | Webhook DLQ + admin replay viewer | 2.4/3.9 | IN | Stripe webhook signature verification present (S5); explicit DLQ + admin replay viewer not enumerated. | MEDIUM | Confirm DLQ + replay exist. Payment reliability depends on it; PAY-020..023 tests require it.
25 | AP-45 | BullMQ job-queue monitor | 3.9 Admin | IN | Queue/cron infra implied; admin queue monitor not listed. | LOW | Confirm or defer.
26 | M-229 | Device fingerprinting (FingerprintJS) | 1.19 Security | IN | Not mentioned; relevant to fraud signals (which are also thin). | MEDIUM | Confirm. Ties to fraud-scoring gap B-48.
27 | AP-46/52(audit) | Immutable audit log + audit viewer | 2.10/3.9 | IN | Audit log present S1; immutability + viewer good. Confirm append-only enforced at DB. | LOW | Confirm immutability (no UPDATE/DELETE as app role). ADM-052 test asserts this.
28 | B-58 | Data retention enforcement (all classes) | 2.10 | IN | Anonymisation 'within retention rules' (S8). Confirm per-class crons (financial 7y, threads 7y, analytics 2y). | LOW | Confirm per-class retention, not just account deletion.

## COVERAGE MAP
COVERAGE MAP — all estimate sections vs booklet
Estimate component / section | In-scope items | Booklet sprint(s) | Coverage | Notes
1.1 Onboarding & Auth | 17 | S1 (BE) + S2 (mobile) | FULL | Email/Google/Apple + tasker OTP. 4 roles only.
1.2 KYC / Identity | 4 | S2 | CHANGED | Stripe Connect handles all identity; no manual ID queue.
1.3 Profile — Poster | 7 | S2 | FULL
1.4 Profile — Tasker | 14 | S2 | FULL | Portfolio/reviews populate S4+S7.
1.5 Task Posting | 22 | S3 | FULL | Text+photo+voice+camera+guest mode.
1.6 Task Discovery | 11 | S4 | FULL | Ranked feed + map + filters.
1.7 Bidding | 10 | S4 | FULL | Incl. licence guard + Builder rule + public Q&A.
1.8 Job Execution | 7 | S6 | FULL | Check-in, completion proof, live location.
1.9 Messaging | 11 | S5 | CHANGED | Single-node Socket.IO; regex moderation not LLM.
1.10 Payments | 17 | S5 | FULL | Mode1+Mode2; Apple/Google Pay.
1.11 Cancellation | 8 | S6 | FULL | Fee matrix.
1.12 Reviews | 7 | S7 | PARTIAL | Blind reveal yes; AI authenticity scoring absent.
1.13 Disputes | 10 | S7 | FULL | Tier-0 Claude Sonnet mediator + admin brief.
1.14 Notifications | 9 | S8 | FULL | Push/email/SMS, Spam Act, fallback.
1.15 Settings | 9 | S2 | FULL | DSR, deletion, prefs.
1.16 Support | 8 | S? / email | PARTIAL | FAQ ok; RAG agent -> email at MVP (deferred).
1.17 Static / Legal | 8 | S11 | FULL | Lawyer review S11.
1.18 Cross-cutting | 18 | S10-S11 | PARTIAL | Polish ok; analytics(217), some items unenumerated.
1.19 Security & Trust Extras | 4 | S1-S2 | PARTIAL | Consent/lockout ok; device fingerprint(M-229) unclear.
2.1 Auth & Users (BE) | 16 | S1 | FULL | NestJS, JWT rotation, RBAC, audit.
2.2 Tasks & Extraction (BE) | 4 | S3 | FULL | Gemini Flash JSON + ReAct + vision.
2.3 Matching Engine | 7 | S4 | FULL | pgvector kNN + ranker + auto-invite.
2.4 Payments (BE) | 14 | S5 | PARTIAL | Core ok; confirm explicit DLQ + replay (B-19/AP-44).
2.5 Messaging (BE) | 6 | S5 | CHANGED | Single-node; regex detection.
2.6 Disputes (BE) | 6 | S7 | FULL | State machine + mediator + brief.
2.7 Notifications (BE) | 5 | S8 | FULL
2.8 Reviews (BE) | 5 | S7 | PARTIAL | Blind/reveal ok; authenticity scoring(B-41) absent.
2.9 File Storage & Media | 5 | S3->S10 | CHANGED | Local FS at MVP -> Azure Blob S10 (migration risk).
2.10 Trust & Safety | 6 | S1/S5/S8 | PARTIAL | Rate-limit/audit/retention ok; FRAUD SCORING(B-48) absent; moderation regex.
3.1 User Management (Admin) | 10 | S9 | FULL | Single admin role.
3.2 Verification Queue | 5 | S4->S9 | CHANGED | Trade-licence review (not identity).
3.3 Job & Booking Mgmt | 9 | S9 | FULL | Force-cancel, manual capture/void, overrides.
3.4 Financial & Payout | 11 | S9 | FULL | Payout tracking, refund, held-funds.
3.5 Disputes (Admin) | 6 | S9 | FULL | Mediation interface + evidence viewer.
3.6 Review Moderation | 3 | S9 | FULL | Manual removal.
3.7 Content & Config | 7 | S9 | FULL | Category/area CRUD, fee/tax config, flags.
3.8 Analytics Dashboard | 5 | S9 | PARTIAL | KPI overview; deep funnel/cohort deferred.
3.9 System / DevOps (Admin) | 5 | S9-S10 | PARTIAL | Webhook log yes; BullMQ monitor(AP-45) unclear.
3.11 Reporting & Analytics | 2 | S9 | PARTIAL | Daily reconciliation; NL builder(AP-52) absent.
3.12 Super User Dashboard | 1 | S9 | CHANGED | Simpler KPI panel vs 24-tile.
3.14 Two-Person Approval | 1 | — | MISSING | No maker-checker (single admin role).
4. Flutter Web | 18 | — | MISSING | No web build in any sprint.
5. Next.js SEO | 18 | — | MISSING | No public SEO site in any sprint.
6.1 LLM Routing & Observability | 5 | S3/S9 | PARTIAL | Router/provider-config ok; OBSERVABILITY+EVAL+QUOTA absent.
6.2 ML Models & Feature Store | 2 | — | MISSING | Feature store + auto-SEO absent.
7.1 CI/CD & Environments | 7 | S0/S10 | FULL | GitHub Actions, staging/prod, migrations.
7.2 Reliability & Observability | 4 | S10 | PARTIAL | App Insights/backups ok; confirm SLA alerting + log PII redaction.
Components fully missing: Flutter Web (18) + Next.js SEO (18) + Feature Store/Auto-SEO (2) + Two-Person (1) = 39 items

## CHANGED ITEMS
CHANGED ITEMS — built differently than estimated
Area | Blueprint / Estimate said | Booklet builds | Why it matters | Confirm?
Admin roles | L1–L7 + Superadmin hierarchy | Single admin role (super-admin post-MVP) | Simplifies RBAC; removes two-person rule basis. Test AUTH-032 collapses to single-vs-super boundary.
KYC / identity | Manual doc review queue + items 21/22 | Stripe Connect handles all identity | Cleanest resolution; eliminates manual queue + CMK docs. Connect states become sole trust-gate.
Moderation | Gemini-Flash LLM classifier | Regex off-platform detection | Regex misses coded/unicode variants; harder to get right. Reframe AIE-004 as regex-coverage + evasion corpus.
Messaging scale | Socket.IO + Redis adapter (multi-node) | Single-node Socket.IO | Won't horizontally scale; MSG-017 multi-instance test N/A. Document scaling limit.
Edge / cloud | Azure Front Door + WAF + APIM | Cloudflare Pro WAF | Different edge stack; WAF/DDoS/bot covered. APIM gateway features absent.
File storage | Azure Blob from start | Local filesystem -> Blob at S10 | Migration-integrity risk at S10; no sensitive data should sit on local disk interim.
Config engine | Versioned, approval-gated platform | Flat admin-editable settings (audited) | Live + audited but no version history / approval gate. ADM-034 depth reduced.
Pen test | Pre-launch (Sprint 13) | Within 60 days POST-launch | HIGHEST RISK: real money + PII flow before adversarial security validation. Recommend scoped pre-launch test of payment+auth+PII.
Super dashboard | 24-tile REST refresh | KPI overview + health panel | Present in spirit; full tile set can follow.
Support | RAG agent (in-app chat) | Email at MVP | Stated deferral; acceptable.
Review authenticity | AI authenticity scoring (B-41) | Manual review removal only | No automated fake-review detection; relies on reports + manual queue.

## TEST IMPACT
TEST IMPACT — how each gap re-points the Master Test Plan v2.0
Gap / change | Test families affected | Action on test suite
Stripe-handled KYC | TC-KYC-003..019 | RETIRE manual-ID, selfie, officer-decision, CMK, PCC-purge, doc-access TCs (mark N/A). KEEP ABN (AUTH-037..039) + Connect-state gating (PAY-026..029).
Single admin role | TC-AUTH-032, TC-ADM-050/051 | Collapse L1–L7 RBAC matrix to single-vs-super. RETIRE two-person TCs unless reinstated.
Regex moderation | TC-MSG-004, TC-BID-003, AIE-004 | Reframe from LLM precision/recall to regex-coverage + add coded/unicode EVASION CORPUS.
Single-node Socket.IO | TC-MSG-017 | Mark multi-instance routing N/A; add single-node load-ceiling test + documented limit.
Local->Blob storage | (new) | ADD S10 migration-integrity test; assert no sensitive data on local disk interim.
AI obs/eval/quota absent | AIE-001..010, NFR-C01 | BLOCKER: AI-eval gates cannot run without AI-03 harness + AI-02 traces. Reinstate or these tests are unexecutable.
Fraud scoring absent | TC-TS-001/002, TC-JOB-004 | Reduce to EXIF + content-safety assertions; mark velocity/device/graph TCs N/A unless B-48 reinstated.
Review authenticity absent | TC-REV-006/007, AIE-008 | Mark authenticity-scoring TCs N/A; keep manual-removal moderation (AP-28) tests.
Flutter Web missing | TC-WEB-001..014 | Mark whole TC-WEB family N/A (parked) unless web reinstated.
Next.js SEO missing | TC-SEO-T01..T12 | Mark whole TC-SEO family N/A (parked) unless SEO reinstated.
Pen test post-launch | TC-NFR-S01..S12 | Re-time security suite. Recommend scoped pre-launch pen test of payment+auth+PII; full suite post-launch.
13-sprint calendar | Execution Overlay | Re-point all surviving TC-IDs onto S0–S12; fold testing into each Friday demo (no dedicated test sprints).

## SIGN-OFF
SCOPE RECONCILIATION — SIGN-OFF
To be completed after the GAP REGISTER is filled and reviewed.
Decision summary (auto-tally once GAP REGISTER filled)
Items reviewed | 28
Marked DEFERRED | 0
Marked DROPPED | 0
Marked COVERED | 0
Marked WILL-ADD | 0
Marked CONFIRM-BUILT | 0
Still TBD / blank | 28
HIGH-severity gaps must be DEFERRED-with-appendix or WILL-ADD before MVP sign-off:
• AI-02 LLM observability
• AI-03 prompt versioning + eval harness
• AI-12 cost quota
• B-48 behavioural fraud scoring
• Pen-test timing (CHANGED tab)
Acceptance
Role | Name | Decision (Accept / Revise) | Date
Founder / Product Owner (Saiju)
Lead Developer
AI Solution Architect
Compliance (tax/privacy)
Once signed: update booklet post-MVP appendix with all DEFERRED/DROPPED items, and update Estimation v1.2 to remove them from MVP totals so all three artifacts agree.